## ProjectSchedule
INVENTORY MANAGEMENT SYSTEM | [6 empty] | ► Watch How to Make a Gantt Chart in Excel
|  | Project Start: | 2024-01-08
Project Lead : SHESHAGIRI S |  | Today: | 2024-02-09
|  | Display Week: | 1 |  |  | 2024-01-08 | [6 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12 | [6 empty] | 2024-02-19 | [6 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11
 | time axis 2024-01-08 to 2024-03-17
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2024-01-08 to 2024-03-17
1. System Requirements:
Conduct user interviews and surveys. | DILEEP | 100% | 2024-01-08 | 2024-01-09 | 2
Define system functionalities and features. | DILEEP | 100% | 2024-01-09 | 2024-01-11 | 3
Document requirements in a formal document. | SHESHAGIRI S | 100% | 2024-01-13 | 2024-01-16 | 4
Create user roles and permission matrix. | DILEEP | 100% | 2024-01-12 | 2024-01-15 | 4
Specify performance and security requirements. | DILEEP | 100% | 2024-01-10 | 2024-01-13 | 4
2. Database Design:
Define entity-relationship diagram (ERD) for data model. | DHANYASHREE | 100% | 2024-01-15 | 2024-01-17 | 3
Design tables for products, categories, suppliers, orders, etc. | SHESHAGIRI S | 100% | 2024-01-17 | 2024-01-17 | 1
Choose and install database software. | DHANYASHREE | 100% | 2024-01-15 | 2024-01-15 | 1
Write PHP code for database connection and queries. | DHANYASHREE | 100% | 2024-01-16 | 2024-01-18 | 3
Establish relationships between tables (e.g., foreign keys). | DHANYASHREE | 100% | 2024-01-18 | 2024-01-20 | 3
3. Product Management Module
Create forms for product data entry and editing. | DIVYA J | 100% | 2024-01-22 | 2024-01-25 | 4
Implement data validation and error handling. | DIVYA J | 100% | 2024-01-23 | 2024-01-24 | 2
Develop product image upload and storage logic. | DIVYA J | 100% | 2024-01-24 | 2024-01-27 | 4
Design category and subcategory hierarchy with selection options. | SHESHAGIRI S | 100% | 2024-01-25 | 2024-01-28 | 4
Implement functions for stock level tracking and reorder point calculations. | DIVYA J | 100% | 2024-01-27 | 2024-01-30 | 4
Write PHP code for database interactions with product data. | DIVYA J | 100% | 2024-01-28 | 2024-01-31
4. Purchase Management Module:
Design purchase order form with product selection and quantity options. | SHESHAGIRI S | 100% | 2024-02-02 | 2024-02-05 | 4
Implement purchase order approval workflow. | SHESHAGIRI S | 90% | 2024-02-06 | 2024-02-08 | 3
Develop supplier management interface with contact details and contracts. | SHESHAGIRI S | 50% | 2024-02-09 | 2024-02-10 | 2
Integrate with supplier APIs (if applicable) for product data. | SHESHAGIRI S | 50% | 2024-02-08 | 2024-02-10 | 3
Write PHP code for purchase order creation, tracking, and cost calculations. | SHESHAGIRI S | 30% | 2024-02-09 | 2024-02-13 | 5
5. Sales Management Module:
Create shopping cart or order form for customer product selection. | DIVYA J | 0% | 2024-02-15 | 2024-02-19 | 5
Implement customer authentication and order placement logic. | DIVYA J | 0% | 2024-02-18 | 2024-02-19 | 2
Integrate with payment gateway for secure transactions. | DIVYA J | 0% | 2024-02-19 | 2024-02-21 | 3
Design discount and promotion rules and application. | DIVYA J | 0% | 2024-02-20 | 2024-02-22 | 3
Develop reports for sales by product, customer, and period. | DIVYA J | 0% | 2024-02-23 | 2024-02-25 | 3
Write PHP code for order processing, payment handling, and reporting. | DIVYA J | 0% | 2024-02-22 | 2024-02-24 | 3
6. Reporting Module:
Design report templates with data visualization options. | SHESHAGIRI S | 0% | 2024-02-24 | 2024-02-25 | 2
Implement report generation logic based on user-defined criteria. | DHANYASHREE | 0% | 2024-02-25 | 2024-02-27 | 3
Allow export of reports to various formats (PDF, CSV, etc.). | DILEEP | 0% | 2024-02-26 | 2024-02-26 | 1
Write PHP code for report data retrieval and formatting. | DILEEP | 0% | 2024-02-27 | 2024-02-29 | 3
7. Security Implementation:
Implement user login and registration features. | SHESHAGIRI S | 0% | 2024-03-05 | 2024-03-07 | 3
Use secure password hashing and storage techniques. | DHANYASHREE | 0% | 2024-03-03 | 2024-03-03 | 1
Encrypt database data and backups. | SHESHAGIRI S | 0% | 2024-03-06 | 2024-03-08 | 3
Validate user input and sanitize data to prevent attacks. | SHESHAGIRI S | 0% | 2024-03-07 | 2024-03-09 | 3
8. User Interface Design & Development:
Design user-friendly interface prototypes for each module. | SHESHAGIRI S | 0% | 2024-03-09 | 2024-03-09 | 1
Develop core UI components with responsive design. | SHESHAGIRI S | 0% | 2024-03-10 | 2024-03-11 | 2
Ensure accessibility for users with | SHESHAGIRI S | 0% | 2024-03-12 | 2024-03-14 | 3
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.