## Sheet1
Department of Collegiate & Technical Education
Capstone project
Format- 7
Weekly Status Report
Capstone project Name: Inventory Management System
Capstone project Members: |  |  | Sheshagiri S
Divya J
Dileep G P
Dhanyashree A P
Week 1 Project Meet Conducted on: /02/2023
Status:
Developing a login and sign up with authentication module of inventory management system
Highlights:
Fix the error for the previous code. And complete the login and sign up module.
Risks or Issues
| Date | Risk or Issue | Description | Resolution | Status
| ---- | Insufficient User Adoption of Login and Signup System | there is a risk that the implemented system may experience insufficient user adoption. This can occur if users find the system too complex, cumbersome, or lacking in value, leading to low registration rates and potential underutilization of the system's features. | Communicate value: Highlight benefits and impact for users. Streamline signup: Minimize steps, offer guidance, and clarify requirements. Prioritize security: Implement strong measures, communicate clear privacy policy, and offer 2FA (if applicable). | 100%
Contd..

## Sheet2
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
| Developing a code of login and sign up | o Complete the code for the login and sign up. o Added CSS to Dashboard. o Fix the error for the previous code. | Sheshagiri s Divya J | 100%
Upcoming Tasks:
| Task Name | Description |  | Team Member Responsible
| Database Design | o Implement database connection and interaction in PHP. o Write PHP code for database connection and queries. o Establish relationships between tables (e.g., foreign keys). o Create a migration files. |  | Sheshagiri s Dileep G P
1)
2)
3)
4)
Date: |  |  | Signature of the students: