## Sheet1
Department of Collegiate & Technical Education
Capstone project
Format- 7
Weekly Status Report
Capstone project Name: Inventory Management System
Capstone project Members: |  |  | Sheshagiri S
Divya J
Dileep G P
Dhanyashree A P
Week 1 Project Meet Conducted on: /02/2023
Status:
Design the database of inventory management system
Highlights:
Write PHP code for database connection and queries.
Risks or Issues
| Date | Risk or Issue | Description | Resolution | Status
| ---- | Inefficient or Incomplete Inventory Management Database Design | There is a risk of creating an inefficient or incomplete database structure. This can lead to several negative consequences, | Stakeholder Involvement: Involve users and stakeholders to understand their data needs and future growth projections. Database Expertise: Engage individuals with strong database design knowledge. Thorough Data Analysis: Conduct a comprehensive analysis of data requirements and relationships. | ----
Contd..
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
Development environment established and configured and learn the necessary programing language.
Upcoming Tasks:
| Task Name | Description | Team Member Responsible
Date: |  |  |  | Signature of the students:

## Sheet2
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
| Database Design | o Implement database connection and interaction in PHP. o Write PHP code for database connection and queries. o Establish relationships between tables (e.g., foreign keys). o Create a migration files. | Dileep G P Sheshagiri S | 100%
Upcoming Tasks:
| Task Name | Description |  | Team Member Responsible
| Create the models and seeder file | o Create the models for the functionality of the inventory management system o Create the seeder file based on the models |  | Divya J
1)
2)
3)
4)
Date: |  |  | Signature of the students: