## Sheet1
Department of Collegiate & Technical Education
Capstone project
Format- 7
Weekly Status Report
Capstone project Name: Inventory Management System
Capstone Project Members: |  |  | Sheshagiri S
Divya J
Dileep G P
Dhanyashree A P
Week 1 Project Meet Conducted on: /02/2023
Status:
Developing a code for inventory management system
Highlights:
Developing a code for product , profile , purchase , supplier , unit module.
Risks or Issues
| Date | Risk or Issue | Description | Resolution | Status
| ---- | Integration Challenges and System Inoperability | There is a significant risk of encountering integration challenges that could lead to system inoperability or malfunctioning functionalities. | Standardized Data Models: Ensure consistency across all modules for smooth data exchange. Strong Communication & Collaboration: Foster collaboration between development teams for clear interfaces and timely issue resolution. Thorough Testing & Validation: Conduct rigorous testing of individual modules and their interaction during integration. | 100%
Contd..

## Sheet2
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
| Developing a code | o write a code for the product module. o write a code for the profile module. o Write a code for the purchase module. o Write a code for the supplier module. o Write a code for the unit module. | Sheshagiri S Divya J Dileep G P Dhanyashree A P | 100%
Upcoming Tasks:
| Task Name | Description |  | Team Member Responsible
| Create a router's file ,vendor file ,HTTP Controller's. | o write a code for the user module. o Create a HTTP Controller's. o Write a code for the router's file. o Create a vendor file |  | Sheshagiri S Divya J Dileep G P Dhanyashree A P
1)
2)
3)
4)
Date: |  |  | Signature of the students: