## Sheet1
Department of Collegiate & Technical Education
Capstone project
Format- 7
Weekly Status Report
Capstone project Name: Inventory Management System
Capstone Project Members: |  |  | Sheshagiri S
Divya J
Dileep G P
Dhanyashree A P
Week 1 Project Meet Conducted on: /02/2023
Status:
Testing and Review the overall project.
Highlights:
Write a test case and test suit . Conduct the unit, integration,non functional testing
Risks or Issues
| Date | Risk or Issue | Description | Resolution | Status
| ---- | Incomplete or Ineffective Test Coverage | During the development of test cases, test suites, and the execution of unit, integration, and non-functional testing, there is a significant risk of incomplete or ineffective test coverage. This can lead to several negative consequences | Test Plan: Develop a well-defined test plan with scope, objectives, and resource allocation. Diverse Testing Team: Assemble a team with varied testing skillsets for comprehensive coverage. Thorough Requirements Analysis: Ensure test cases align with user requirements and address potential use cases. Multiple Testing Techniques: Utilize various techniques (black-box, white-box, exploratory) to maximize coverage. Risk-Based Testing: Prioritize testing based on potential impact and identified risks. | ----
Contd..

## Sheet2
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
| Testing and Review | o Fix the error and Debug the error. o write a test case and test suit. o Conduct the unit testing and integration testing o Conduct the system testing and non functional testing | Sheshagiri S Divya J Dileep G P Dhanyashree A P | 100%
Upcoming Tasks:
| Task Name | Description |  | Team Member Responsible
| Testing and Review | o Fix the error and Debug the error. o write a test case and test suit. o Conduct the unit testing and integration testing o Conduct the system testing and non functional testing |  | Sheshagiri S Divya J Dileep G P Dhanyashree A P
1)
2)
3)
4)
Date: |  |  | Signature of the students: