## Sheet1
Department of Collegiate & Technical Education
Capstone project
Format- 7
Weekly Status Report
Capstone project Name: Inventory Management System
Capstone project Members: |  |  | Sheshagiri s
Divya j
Dileep
Dhanyashree A P
Week 1 Project Meet Conducted on: /02/2023
Status:
Collecting a System Requirements of inventory management system
Highlights:
Gather user requirements through interviews, surveys, or workshops.
Risks or Issues
| Date | Risk or Issue | Description | Resolution | Status
| ---- | Incomplete or Inaccurate System Requirements | During the stage of collecting system requirements for the inventory management system, there is a risk that the gathered information might be incomplete or inaccurate. This can lead to a system that does not meet the actual needs of the users, resulting in inefficiencies, rework, and additional costs. | Engage stakeholders: Interviews, workshops, user stories. Define & Document: User stories, use cases, central repository. Validate & Refine: Reviews, prototypes, iterative approach. Communication & Collaboration: Clear channels, open dialogue. | completed
Contd..
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
Development environment established and configured and learn the necessary programing language.
Upcoming Tasks:
| Task Name | Description | Team Member Responsible
Date: |  |  |  | Signature of the students:

## Sheet2
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
| System Requirements | o Gather user requirements through interviews, surveys, or workshops. o Analyze requirements to identify functional and non-functional needs. | Sheshagiri s Divya j | 100%
Upcoming Tasks:
| Task Name | Description |  | Team Member Responsible
| Define the System Requirements | o Define system functionalities and features. o Document requirements in detail with specifications and use cases. o Document the Work break down system |  | Sheshagiri s Divya j Dileep Dhanyashree A P
1)
2)
3)
4)
Date: |  |  | Signature of the students: