## Sheet1
Department of Collegiate & Technical Education
Capstone project
Format- 7
Weekly Status Report
Capstone project Name: Inventory Management System
Capstone project Members: |  |  | Sheshagiri s
Divya j
Dileep
Dhanyashree A P
Week 1 Project Meet Conducted on: /02/2023
Status:
Defining a System Requirements of inventory management system
Highlights:
1) Calcuate the time and cost expenses and Choose appropriate technology stack (framework, database).
Risks or Issues
| Date | Risk or Issue | Description | Resolution | Status
| ---- | Inaccurate Time and Cost Estimates | During the stage of calculating time and cost expenses for the project, there is a risk that the estimates may be inaccurate. This can lead to several negative consequences | Buffer & reviews: Allocate buffer in budget/timeline and regularly review estimates. Project management tools: Utilize tools for tracking progress and potential deviations. | 100%
Contd..
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
Development environment established and configured and learn the necessary programing language.
Upcoming Tasks:
| Task Name | Description | Team Member Responsible
Date: |  |  |  | Signature of the students:

## Sheet2
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
| Define the time frame and cost expenses | o Calcuate the time and cost expenses for overall project. o Choose appropriate technology stack (framework, database). o Design database schema with tables, relationships, and data types. | Sheshagiri s Divya j | 100%
Upcoming Tasks:
| Task Name | Description |  | Team Member Responsible
| Developing a code of Dashboard | o Define the architecture diagram. o Start the project by writing a code of dashboard. |  | Sheshagiri s Divya j
1)
2)
3)
4)
Date: |  |  | Signature of the students: