## Sheet1
Department of Collegiate & Technical Education
Capstone project
Format- 7
Weekly Status Report
Capstone project Name: Inventory Management System
Capstone project Members: |  |  | Sheshagiri s
Divya j
Dileep
Dhanyashree A P
Week 1 Project Meet Conducted on: /02/2023
Status:
Set up the visual studio and Introduction to HTML and CSS
Highlights:
Creating a sample web pages using HTML and CSS
Risks or Issues
| Date | Risk or Issue | Description | Resolution | Status
| ---- | ---- | ---- | ---- | ----
Contd..
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
Upcoming Tasks:
| Task Name | Description | Team Member Responsible
Date: |  |  |  | Signature of the students:

## Sheet2
Tasks in Progress or Completed:
| Task Name | Description | Team Member Responsible | Percentage Complete
| Development environment established and configured and learn the necessary programing language. | Visual studio and other supporting extensions have been downloaded and installed on the development machine. And learn the necessary Programing languages including ( HTML and CSS ) | Sheshagiri s Divya j Dileep Dhanyashree A P | 100%
Upcoming Tasks:
| Task Name | Description |  | Team Member Responsible
| Development environment established and configured and learn the necessary programing language. | Visual studio and other supporting extensions have been downloaded and installed on the development machine. And learn the necessary Programing languages including ( HTML and CSS ) |  | Sheshagiri s Divya j Dileep Dhanyashree A P
1)
2)
3)
4)
Date: |  |  | Signature of the students: